AI Technical Program Manager — UST

Week 1 · Exercise 2 · Answer Workbook

Kestrel Health Network — "Beacon" AI-assisted patient triage. Your answer file for Exercise 2. Fill it in as you go, then submit this same file.

For: every participant. Individual exercise. Save your own copy before you start typing.

File name for your copy: UST_AITPM_Week1_Ex2_Workbook_Robin Cherian_U11910

Used with: Week 1 · Exercise 2 · Case Pack (Kestrel Health Network / Beacon). There is no Lab Kit for this exercise; this file holds only the forms. Suggested time: 3 to 4 hours.

# Part 1 · Cover block

| Field | Your entry |
| --- | --- |
| Candidate id | U11910 – Robin Cherian |
| Week | Week 1 · Exercise 2 · Release-Readiness Checklist v1 (Beacon) |
| Domain track used | Healthcare (Kestrel Health Network) |
| AI tool(s) used | Claude / Copilot. Not scored; for the facilitator's interest only |
| Attempt number | 1 |
| Date submitted | 29-10-2026 |

# Part 2 · Findings Log

Record every weakness in checklist v0.9 that would stop a careful stranger trusting that Beacon is ready. Aim for 15 or more findings, with at least one for each of the five dimensions.

Category: use one or more of Dimension gap · Ownership · AI control · Stage gate · Evidence · Contradiction. Severity: Critical · High · Medium · Low. Mapped control: the Part 4b criterion ID (for example AI-01) or the Part 3 table the finding maps to. Evidence reference: the Case Pack part and item, for example "E1, report footer" or "E4, 26 Nov message".

| # | v0.9 item(s) | Finding (what is wrong) | Category | Severity | Mapped control | Why it matters (for the sponsor) | Evidence reference | What v1 must contain instead |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| F1 | 9 | Item 9 "Model validated (96% accuracy)" is ticked on the Corvid validation summary: 96.2% on CorvidBench-Triage, 48,000 primary-care messages from the United States and United Kingdom. Kestrel's own evaluation shows 0.93 on Kestrel messages, and the owner, Jonas Weber, left Kestrel on 16 October. | Evidence; Contradiction | Critical (Both) | Q-01 | AIP-2 requires evaluation on Kestrel data, so a supplier benchmark on other countries' messages cannot validate Beacon for Kestrel patients. | E2; E1, row "Urgency category accuracy" (0.93); A3 (Jonas Weber, no longer with Kestrel); A4, AIP-2 | Q-01: Beacon validated on Kestrel data for the release build, model and threshold, signed by Dr. Farah Siddiqui and approved by Dr. Helen Mathews. Supplier results recorded as an input only. |
| F2 | 10; Appendix (threshold note) | Item 10 says the threshold is 0.80, but triage-config.yaml sets auto_route_threshold: 0.72, lowered on 25 Nov "to reduce nurse queue". Imran Qureshi made the change without re-evaluation ("Eval numbers will be basically the same"), and the appendix says the threshold "may be tuned operationally by Engineering". | AI control; Contradiction | Critical (Both) | AI-01 | A lower threshold sends more messages past the nurse with no human check, and AIP-2 requires re-evaluation on Kestrel data and CSO approval before any threshold change is used. | E3, triage-config.yaml (auto_route_threshold, commit a41f, 26 Nov); E4, 26 Nov (Imran Qureshi); E1 footer (threshold 0.80); Appendix threshold note; A4, AIP-2 | AI-01: one threshold value, evaluated on Kestrel data at that value and approved in writing by Dr. Helen Mathews; configuration matches the approved value; any change follows AIP-2, never operational tuning by Engineering. Owner Dr. Farah Siddiqui. |
| F3 | 11 | Item 11 "Clinical safety case signed" rests on hazard log v2, written and signed by Corvid AI's Clinical Safety Officer for CorvidBench deployments. It has no hazards for automated replies to patients, mixed-language messages or nurse queue capacity. Kestrel's CSO, Dr. Helen Mathews, has not been asked to review it, and the item is owned by the Delivery Lead. | Contradiction; Dimension gap (Governance) | Critical (Both) | G-01 | CSS-1 requires a Kestrel safety case and hazard log signed by Kestrel's CSO, so Beacon has no valid clinical safety case for the pilot. | E7; E2; A5, Spec row (safety section copied from Corvid's hazard log); A4, CSS-1; A3 (Dr. Helen Mathews) | G-01: Kestrel clinical safety case and hazard log covering automated replies, mixed-language messages and nurse queue capacity, owned and signed by Dr. Helen Mathews. Corvid's hazard log referenced as an input only. |
| F4 | 14 | Item 14 "DPIA approved" rests on DPIA v1 from August, which covers referral letters only. Portal messages were added to scope on 9 October, and the DPO says an addendum is needed before patient messages are processed. | Contradiction; Dimension gap (Governance) | Critical (Both) | G-03 | The pilot processes portal messages from day one, which goes beyond what the data protection assessment has approved. | E4, 2 Dec (Grace Liu); A5, Intent row; Part B item 14 | G-03: DPIA addendum covering portal messages and automated replies, approved by Grace Liu before 14 December. |
| F5 | 16 | Item 16 "Accessibility review" is marked N/A as a "Backend service", but Beacon sends automated self-care replies to patients. ev-118 measured those replies at reading level Grade 11, and whether replies are offered in Hindi and Marathi is not evidenced. | Contradiction; Dimension gap (Governance) | Critical (Both) | G-06 | PCS-3 requires grade 8 or below in the patient's chosen language, so Grade 11 replies breach the standard and may not be understood by the patients they advise. | E1, row "Reading level of automated self-care replies" (Grade 11); A2 (automated reply); A4, PCS-3 | G-06: sample of automated replies at grade 8 or below in English, Hindi and Marathi, checked against PCS-3 and approved by Dr. Helen Mathews. Owner Dr. Farah Siddiqui. |
| F6 | 17 | Item 17 says urgent cases reach the nurse queue with a 30-minute response. On the night shift two triage nurses cover both pilot sites and the ward phone line; in the simulation the urgent queue peaks at about 25 cases between 7 and 10 pm, which at about 6 minutes per case takes 75 minutes to clear. | AI control; Contradiction | Critical (Both) | AI-02 | Urgent and emergency patients could wait more than twice the stated response time, and the threshold change to 0.72 alters the queue the nurses receive. | E4, 1 Dec (Priyanka Das); Part B item 17; E1, row "Messages auto-routed at threshold 0.80" (31% to nurse queue) | AI-02: trigger (Emergency, Urgent or below threshold), receiving role (triage nurse), time limit, and evidence that night-shift capacity meets the limit at the approved threshold. Owner Priyanka Das. |
| F7 | 18 | Item 18 says R-17 (mixed-language under-triage) was accepted on 5 Dec. It was accepted by Neha Sharma "on behalf of delivery so we stay green for Thursday", and Owen Fletcher recorded it as "accepted (N. Sharma, 5 Dec)". | Contradiction; Ownership | Critical (Both) | G-02 | AIP-2 allows only the CMO or the CSO to accept a clinical AI risk, in writing with a review date, so the 6.8% mixed-language under-triage risk has not been validly accepted. | E4, 5 Dec (Neha Sharma) and 7 Dec (Owen Fletcher); E1, row mixed-language (6.8%, risk R-17); A4, AIP-2 | G-02: every clinical risk, including R-17, accepted or rejected in writing by Dr. Anjali Rao or Dr. Helen Mathews with a review date, recorded in the enterprise risk register. Owner Owen Fletcher. |
| F8 | 19 | Item 19 "Monitoring and drift dashboard live" points to the Grafana "Beacon Drift" dashboard. Its baseline is the CorvidBench supplier benchmark, no Kestrel baseline is loaded, no under-triage measure exists in production, and no clinician sampling of auto-routed messages is scheduled. | AI control; Evidence | Critical (Both) | AI-03 | Urgent messages routed as routine or self-care would go undetected, because nothing measures under-triage after go-live. | E5, bullets 1 to 3 | AI-03: drift monitor with a Kestrel baseline, an under-triage measure from scheduled clinician sampling of auto-routed messages, numeric bands, alert routing, a named responder and a breach action. Owner Kavya Nair. |
| F9 | 21 | Item 21 "Audit logging enabled" is ticked on log_fields in triage-config.yaml, which logs message_id, category and confidence only. The rationale, model version, prompt version, threshold, routing action, reply text and any nurse override are not logged. | Evidence; Dimension gap (Governance) | Critical (Both) | G-04 | RP-1 requires the record of every decision about a patient's care, so Beacon's decisions could not be reconstructed or explained. | E3, triage-config.yaml (log_fields); A4, RP-1 | G-04: decision record with category, confidence, rationale, model version, prompt version, threshold, routing action, reply text and nurse override, with one decision reconstructed end to end. Owner Kavya Nair. |
| F10 | 22 | Item 22 "Data retention configured" is ticked on 365 days, matching retention_days: 365 in the configuration. RP-1 requires 8 years, and the owner is "Platform / Nursing (joint)". | Contradiction; Ownership | Critical (Both) | G-05 | Patient communications and decision records would be deleted after one year, breaching RP-1. | E3, triage-config.yaml (retention_days: 365); A4, RP-1; Part B item 22 | G-05: retention set to 8 years for patient communications and decision records, with the configuration export as evidence. Owner Kavya Nair. |
| F11 | 25; Missing line (patient escalation) | Item 25 "Contact centre briefed" rests on an email with a link to the release notes: no call scripts and no route for patients who say their symptoms are worse. When a patient replies "it's getting worse" to a self-care reply, the message lands in the general inbox, which is answered within 48 hours. | Dimension gap (Operational); AI control | Critical (Both) | O-03; AI-02 | A deteriorating patient who was sent self-care advice could wait up to 48 hours before anyone sees the message. | E4, 3 Dec (Sunil Bhat); E8, Contact centre (item 25) | O-03: any patient reply to an automated message routed to the triage nurse queue, plus contact-centre call scripts for worsening symptoms, approved by Priyanka Das. Owner Sunil Bhat. |
| F12 | 26 | Item 26 "Patient communication (AI disclosure) approved" is ticked, but the wording is a draft sent to Legal for review, in English only. | Contradiction; Dimension gap (Governance) | Critical (Both) | G-07 | PCS-3 requires patients to be told when a message was drafted by an automated system, in their chosen language, so replies sent from 14 December would breach it. | E8, Patient AI disclosure (item 26); A4, PCS-3 | G-07: approved AI-disclosure wording in English, Hindi and Marathi, present in every automated reply, approved by Dr. Anjali Rao. Owner Marcus Bell. |
| F13 | 27 | Item 27 says Corvid notifies 14 days ahead. Beacon calls the floating alias corvid-med-latest, which Corvid will move to corvid-med-3.3 on 15 December, the day after the pilot starts. Kestrel chose the alias although pinned versions are available, and ev-118 tested corvid-med-3.2. | Contradiction; Dimension gap (Technical) | Critical (Both) | T-04 | AIP-2 requires re-evaluation on Kestrel data and CSO approval before a model change is used; the supplier's "non-material" label is a claim, not that approval. | E3 (model: corvid-med-latest); E4, 30 Nov (Corvid AI notice); E8, Vendor change process (CTR-311, clause 9.4); E1 footer (corvid-med-3.2); A4, AIP-2 | T-04: Beacon pinned to an evaluated model version; any supplier model change re-evaluated on Kestrel data and approved by Dr. Helen Mathews before use. Owner Imran Qureshi. |
| F14 | 30; Appendix (stage-gate approvals) | Item 30 calls the Go/No-Go a "formality" because all stage gates are approved. The appendix shows every gate (Intent, Spec, Plan, Build, Review) approved by Neha Sharma on 2 December, including the gates covering the spec and the clinical safety case. | Stage gate; Ownership | Critical (Both) | Table 3b | One person approving every gate on one day, including clinical safety, means no gate had an independent check, so the gates are not evidence. | Appendix notes (stage-gate approvals); Part B item 30; A3 (Neha Sharma) | Table 3b: an independent named approver per stage and dimension (for example Dr. Helen Mathews for clinical safety) with the artefact reviewed; the Go/No-Go confirms gates already passed. |
| F15 | Missing line (evaluation currency) | ev-118 evaluated build 1.4.0, model corvid-med-3.2 and threshold 0.80, and its clinical safety review is pending. The release is build 1.4.2 at threshold 0.72, on an alias that moves to corvid-med-3.3 on 15 December. | Evidence; Stage gate | Critical (Both) | Q-01 | No evaluation covers the build, model and threshold that would run in the pilot, which AIP-2 requires before use. | E1 footer; A5, Build row; E3; E4, 30 Nov (Corvid AI notice) | Q-01: Kestrel evaluation on the exact release build, model version and threshold, reviewed by Dr. Helen Mathews. Owner Dr. Farah Siddiqui. |
| F16 | Missing line (under-triage acceptance) | No checklist line sets an acceptable under-triage rate. ev-118 shows 2.1% overall, 1.6% for English-only messages and 6.8% for mixed-language or transliterated messages, more than four times the English-only rate. | Dimension gap (Quality); AI control | Critical (Both) | Q-02 | Under-triage is the safety-critical measure, and patients writing in Hindi, Marathi or mixed script face the highest risk of an urgent case being auto-routed. | E1, under-triage rows; A1 (languages) | Q-02: an under-triage acceptance criterion for all messages and for each language subgroup, approved by Dr. Helen Mathews, with evaluation results against it. Owner Dr. Farah Siddiqui. |
| F17 | 1, 3 | The business case (August) and intent.md cover GP referral letters only. Portal messages and automated replies were added on 9 October by a decision in the team channel, intent.md was not updated, and spec v3 with the wider scope was approved by the Delivery Lead, Neha Sharma, on 2 December. | Stage gate; Dimension gap (Business) | High (Both) | B-01 | The pilot includes patient-facing features that no approved intent or business case covers, so nobody with authority has agreed the scope going live. | A5, Intent and Spec rows; Part B items 1 and 3 | B-01: intent.md and the business case updated for portal messages and automated replies, approved by Marcus Bell and Dr. Anjali Rao. |
| F18 | 4 | ADR-009, the architecture approval, is dated 21 September. Portal messages and automated replies were added on 9 October, and there is no later architecture review. | Stage gate; Dimension gap (Technical) | High (Both) | T-01 | The integration for portal messages and automated replies has not been architecturally reviewed. | E8, Architecture (item 4) | T-01: architecture review covering portal messages and automated replies, signed before 14 December. Owner Tobias Grant, with the record handed to Imran Qureshi before 18 December. |
| F19 | 4, 15, 23; Appendix (ownership note) | Tobias Grant owns architecture (item 4), the load test (item 15) and rollback (item 23), and the appendix says technical items are his "until handover". His contract ends on 18 December, four days into the pilot and before the network rollout, and no successor is named. | Ownership | High (Both) | Table 3a | From 18 December no named person would own the architecture, load and rollback evidence, including during the pilot itself. | A3 (Tobias Grant, contract ends 18 Dec); Appendix ownership note; Part B items 4, 15, 23 | Table 3a: a named Kestrel person from A3 as owner of each item Tobias holds, with handover completed and recorded before 18 December. |
| F20 | 6 | Item 6 "Feature plans complete" is ticked, but plans exist for 9 of 11 features. "Automated reply drafting" and "threshold tuning" have no plan; Imran describes them as "small config features". | Stage gate; Contradiction | High (Both) | T-02 | The two unplanned features decide which patients bypass a nurse and what advice they receive. | A5, Plan row; Part B item 6 | T-02: approved plans for all 11 features, including automated reply drafting and threshold tuning, with clinical features approved by Dr. Helen Mathews. Owner Imran Qureshi. |
| F21 | 8, 9, 11, 16, 22 | Several v0.9 owners cannot be accountable: Jonas Weber (items 8 and 9) left Kestrel on 16 October; item 22 is owned by "Platform / Nursing (joint)"; and the Delivery Lead owns the clinical safety case (item 11), which CSS-1 assigns to the CSO, and accessibility (item 16). | Ownership | High (Both) | Table 3a | A leaver, a joint team or a person without the authority cannot be held to the evidence, and the pack's ownership rules forbid them. | A3 (ownership rules; no longer with Kestrel); Part B owner column; A4, CSS-1 | Table 3a: one named person from A3 per line, for example Victor Osei for test items and Dr. Helen Mathews for clinical safety. |
| F22 | 12 | Item 12 "Code review complete" counts 87 of 87 PRs approved. Twelve were approved by Imran Qureshi, who also wrote the prompts the coding agent used to produce them, and about 70% of the code was written by coding agents. | Evidence; Dimension gap (Technical) | High (Both) | T-03 | Twelve changes had no independent human review, in code mostly written by agents. | A5, Build and Review rows; Part B item 12 | T-03: independent human review for every PR, with the 12 re-reviewed by an engineer who did not write their prompts, approved by Victor Osei. Owner Neha Sharma. |
| F23 | 15 | Item 15 passed at 3× pilot volume (p95 1.8 s on build 1.4.2). The checklist also covers the network rollout to all nine hospitals, which has not been load tested. | Dimension gap (Technical); Stage gate | High (Network) | T-05 | The test supports the pilot but not the 11 January rollout to all nine hospitals. | Part B item 15 (LT-1.4.2, 1 Dec); Appendix (checklist covers pilot and network) | T-05: load test at network volume before 11 January. Owner Kavya Nair. |
| F24 | 20 | Item 20 "Alerts configured" points to the #beacon-alerts channel. The channel has 14 members and is not on any on-call rota; the platform rota is paged only for infrastructure alerts. | Dimension gap (Operational); Evidence | High (Both) | O-01 | A drift or safety alert out of hours would reach a chat channel with nobody obliged to respond. | E5, bullet 4; E3 (alert_channel) | O-01: drift and safety alerts routed to a named on-call responder with a response time. Owner Kavya Nair. |
| F25 | 23 | Item 23 "Rollback rehearsed" rolled back the application container from 1.4.2 to 1.3.9 in 4 minutes. The runbook does not cover the model version (called through corvid-med-latest), the prompt version, or switching Beacon off so all messages go to nurses. | Dimension gap (Operational); Evidence | High (Both) | T-06 | If the model or a prompt changes behaviour, there is no tested way to undo it or return to manual triage. | E6 | T-06: rehearsed rollback for application, model version and prompt version, plus a tested switch-off to manual triage with a named decision-maker. Owner Kavya Nair. |
| F26 | 24 | Item 24 "Triage nurses trained" is ticked on "E-learning module assigned". On 7 December, 11 of 29 pilot-site triage nurses (38%) had completed it. | Contradiction; Dimension gap (Operational) | High (Both) | O-02 | Most of the nurses who receive Beacon's cases have not completed the training. | E8, Nurse training (item 24) | O-02: completion record for all pilot-site triage nurses before 14 December, and for network nurses before 11 January. Owner Priyanka Das. |
| F27 | 28; Appendix (scope note) | Item 28 is ticked on Rollout plan v2, and the appendix says the network rollout proceeds per that plan once the pilot Go/No-Go passes. There is no separate network gate and no criterion based on pilot results. | Stage gate | High (Network) | Table 3c | The rollout to all nine hospitals would go ahead on 11 January without anyone checking what the pilot showed. | Part B item 28; Appendix notes; A2 (two-phase rollout) | Table 3c: a separate network gate before 11 January, using pilot evidence (under-triage, queue times, incidents), approved by Dr. Anjali Rao. |
| F28 | 8 | Item 8 "Regression suite green" is real (CI run #2291 on build 1.4.2), but the QA Manager notes that the suite does not include the model evaluation set. | Evidence | Medium (Both) | Q-03 | A green regression run shows the code works, not that Beacon triages correctly. | E4, 27 Nov (Victor Osei) | Q-03: regression results recorded separately from model evaluation (Q-01). Owner Victor Osei. |
| F29 | All (stage column) | v0.9 uses "Release" as its sixth stage instead of Deploy, and the Release gate is recorded as "at Go/No-Go". The deploy artefacts in A5 (pipeline logs, staging, monitoring) are not referenced. | Stage gate | Low (Both) | Table 3b | The naming makes it harder to trace checklist lines to the artefact chain, though it does not change any result. | Part B stage column; Appendix notes; A5, Deploy row | Table 3b and Part 4b: stages named Intent, Spec, Plan, Build, Review, Deploy, with deploy artefacts cited. |

# Part 3 · Governance frame

Decide the structure of your checklist before you write it.

## 3a. Who owns each dimension?

Exactly one Accountable person per dimension, by name, from Case Pack Part A3 (no teams, no suppliers, nobody who has left). One person may own two dimensions; one dimension never has two Accountables. Test each with the Saturday question: if this fails on go-live weekend, is this the person whose phone rings?

| Dimension | Accountable (one named person) | Responsible | Consulted | Informed | Why this person (one sentence) |
| --- | --- | --- | --- | --- | --- |
| Business | Marcus Bell | Neha Sharma | Dr. Helen Mathews, Priyanka Das | Dr. Anjali Rao | As Chief Digital Officer he owns the business case and budget and is in post for both phases, so he answers for whether the scope going live is the scope that was approved. |
| Technical | Neha Sharma | Imran Qureshi | Tobias Grant (until 18 Dec 2026), Rahul Menon, Kavya Nair | Marcus Bell | As Delivery Lead she runs the delivery team through both phases, so a technical failure on go-live weekend is hers to act on, but she approves none of her own team's gates (see 3b). |
| Quality | Victor Osei | Dr. Farah Siddiqui | Dr. Helen Mathews | Neha Sharma | As QA Manager who has owned the test strategy since November, he is independent of the evaluation's author and in post for both phases, so he answers for whether the evidence proves Beacon works. |
| Governance | Dr. Helen Mathews | Owen Fletcher | Grace Liu, Rahul Menon | Dr. Anjali Rao | As Clinical Safety Officer she is the only person besides the CMO who can sign the safety case and accept clinical AI risk under CSS-1 and AIP-2, so a clinical governance failure is hers to act on. |
| Operational | Priyanka Das | Kavya Nair | Sunil Bhat, Dr. Farah Siddiqui | Dr. Anjali Rao | As Head of Nursing she manages the triage nurses who receive every case Beacon does not route, so if the queue or a misrouted patient fails on go-live weekend she can redeploy staff and act. |

## 3b. Where is each dimension checked? (stage-gate map)

In each cell where a gate exists, write who approves crossing it and the artefact they look at, for example "Approver: name · Artefact: signed eval report". Leave the cell empty where there is no gate. Use all six stages; at least three dimensions should have gates at more than one stage.

| Dimension | Intent | Spec | Plan | Build | Review | Deploy |
| --- | --- | --- | --- | --- | --- | --- |
| Business | Approver: Dr. Anjali Rao · Artefact: beacon/intent.md and business case updated for portal messages and automated replies (B-01) |  |  |  |  | Approver: Dr. Anjali Rao · Artefact: pilot Go/No-Go decision record, and a separate network gate record before 11 Jan 2027 using pilot evidence (Table 3c) |
| Technical |  | Approver: Kavya Nair · Artefact: architecture review covering portal messages and automated replies, superseding ADR-009 (T-01) | Approver: Dr. Helen Mathews · Artefact: beacon/plans/ for automated reply drafting and threshold tuning (T-02) | Approver: Dr. Helen Mathews · Artefact: triage-config.yaml with a pinned, evaluated model version and the approved auto_route_threshold (T-04, AI-01) | Approver: Victor Osei · Artefact: independent re-review record for the 12 PRs approved by Imran Qureshi (T-03) | Approver: Victor Osei · Artefact: rollback rehearsal record covering application, model version, prompt version and manual-triage switch-off; network-volume load test (T-06, T-05) |
| Quality |  | Approver: Dr. Helen Mathews · Artefact: under-triage acceptance criteria, overall and per language subgroup (Q-02) | Approver: Victor Osei · Artefact: test strategy separating the regression suite from model evaluation (Q-03) | Approver: Dr. Helen Mathews · Artefact: Kestrel evaluation replacing ev-118, on build 1.4.2 with the pinned model and approved threshold (Q-01) | Approver: Victor Osei · Artefact: evaluation results against the Q-02 criteria, traced to the release configuration in triage-config.yaml (Q-01, Q-02) |  |
| Governance |  | Approver: Grace Liu · Artefact: DPIA addendum covering portal messages and automated replies (G-03) |  | Approver: Owen Fletcher · Artefact: triage-config.yaml log_fields for the full decision record and an 8-year retention export (G-04, G-05) | Approver: Dr. Helen Mathews · Artefact: Kestrel clinical safety case and hazard log signed by her; R-17 and other clinical risks accepted in writing with review dates; reply sample at grade 8 or below in English, Hindi and Marathi (G-01, G-02, G-06) | Approver: Dr. Anjali Rao · Artefact: approved AI-disclosure wording in English, Hindi and Marathi in every automated reply (G-07) |
| Operational |  | Approver: Dr. Helen Mathews · Artefact: human-in-the-loop trigger, time limit and night-shift capacity model at the approved threshold (AI-02) | Approver: Priyanka Das · Artefact: route sending patient replies to automated messages into the triage nurse queue, and contact-centre call scripts (O-03, AI-02) | Approver: Dr. Farah Siddiqui · Artefact: Beacon Drift dashboard with a Kestrel baseline, an under-triage sampling measure and numeric bands (AI-03) |  | Approver: Dr. Anjali Rao · Artefact: training completion record for pilot-site triage nurses and a named on-call rota for drift and safety alerts (O-02, O-01) |

## 3c. What must be true at the pilot gate versus the network gate?

For each dimension, write what must be true before the pilot goes live at Kestrel Riverside and Kestrel Hillcrest on 14 December 2026, and what must additionally be true before the network rollout to all nine hospitals on 11 January 2027.

| Dimension | Pilot gate — 14 Dec 2026 (Riverside, Hillcrest) | Network gate — 11 Jan 2027 (all nine hospitals) |
| --- | --- | --- |
| Business | 1. beacon/intent.md and the business case cover portal messages and automated replies, approved by Dr. Anjali Rao (B-01). Confirms: Dr. Anjali Rao. 2. The Go/No-Go decision is recorded, with an owner and a check date for every condition (Table 3b). Confirms: Dr. Anjali Rao. | 1. A separate network gate is held before 11 Jan 2027, using the pilot evidence in this column (Table 3c). Confirms: Dr. Anjali Rao. 2. Rollout plan v2 is updated with the pilot results before it is approved (B-01). Confirms: Marcus Bell. |
| Technical | 1. triage-config.yaml pins an evaluated model version in place of corvid-med-latest (T-04). Confirms: Dr. Helen Mathews. 2. auto_route_threshold equals the value evaluated and approved under AI-01 (AI-01). Confirms: Dr. Helen Mathews. 3. Architecture review covering portal messages and automated replies is signed (T-01). Confirms: Kavya Nair. 4. The 12 PRs approved by Imran Qureshi are re-reviewed independently (T-03). Confirms: Victor Osei. 5. Rollback is rehearsed for application, model version, prompt version and manual-triage switch-off (T-06). Confirms: Victor Osei. 6. Every item Tobias Grant owns has a named Kestrel owner from A3, with handover recorded before 18 Dec 2026 (Table 3a). Confirms: Neha Sharma. | 1. Load test passes at network volume for all nine hospitals (T-05). Confirms: Victor Osei. 2. Any model, prompt or threshold change since the pilot, including Corvid's move to corvid-med-3.3, is re-evaluated on Kestrel data and approved before use (T-04, AI-01). Confirms: Dr. Helen Mathews. 3. Rollback and manual-triage switch-off are rehearsed again by the new owner after Tobias Grant's exit (T-06). Confirms: Victor Osei. |
| Quality | 1. A Kestrel evaluation on build 1.4.2, with the pinned model and approved threshold, replaces ev-118 (Q-01). Confirms: Dr. Helen Mathews. 2. Under-triage meets the Q-02 criteria overall and for mixed-language or transliterated messages (Q-02). Confirms: Dr. Helen Mathews. 3. Regression results are recorded separately from model evaluation (Q-03). Confirms: Victor Osei. | 1. A clinician sample of auto-routed pilot messages shows under-triage within the Q-02 criteria, overall and per language subgroup (Q-02, AI-03). Confirms: Dr. Helen Mathews. 2. The evaluation is repeated if the build, model or threshold changed during the pilot (Q-01). Confirms: Victor Osei. |
| Governance | 1. Kestrel clinical safety case and hazard log, covering automated replies, mixed-language messages and nurse queue capacity, are signed by Dr. Helen Mathews (G-01). Confirms: Dr. Helen Mathews. 2. R-17 is accepted or rejected in writing by Dr. Anjali Rao or Dr. Helen Mathews, with a review date, in the risk register (G-02). Confirms: Owen Fletcher. 3. DPIA addendum covering portal messages is approved (G-03). Confirms: Grace Liu. 4. The full decision record is logged and retention is set to 8 years (G-04, G-05). Confirms: Owen Fletcher. 5. Automated replies are at grade 8 or below in English, Hindi and Marathi (G-06). Confirms: Dr. Helen Mathews. 6. AI-disclosure wording is approved in English, Hindi and Marathi (G-07). Confirms: Dr. Anjali Rao. | 1. The hazard log is updated with pilot incidents and re-signed (G-01). Confirms: Dr. Helen Mathews. 2. Every clinical risk review date falling before 11 Jan 2027 has been met (G-02). Confirms: Owen Fletcher. 3. The DPIA is confirmed to cover all nine hospitals (G-03). Confirms: Grace Liu. |
| Operational | 1. Night-shift nurse capacity at both pilot sites meets the AI-02 time limit at the approved threshold (AI-02). Confirms: Priyanka Das. 2. Patient replies to automated messages go to the triage nurse queue, and contact-centre scripts are in use (O-03). Confirms: Priyanka Das. 3. The drift monitor is live with a Kestrel baseline, scheduled under-triage sampling, numeric bands and alert routing (AI-03). Confirms: Dr. Farah Siddiqui. 4. Drift and safety alerts page a named on-call responder (O-01). Confirms: Kavya Nair. 5. All 29 pilot-site triage nurses have completed training (O-02). Confirms: Priyanka Das. | 1. Triage nurses at all nine hospitals have completed training (O-02). Confirms: Priyanka Das. 2. Night-shift capacity is modelled for each of the nine hospitals at the approved threshold (AI-02). Confirms: Priyanka Das. 3. Pilot queue times and drift alerts have been reviewed, with no unresolved breach (AI-02, AI-03). Confirms: Dr. Farah Siddiqui. |
| 3d. What is the 10 December Go/No-Go meeting for now? (one sentence) The 10 December Go/No-Go meeting confirms, against the evidence recorded at each gate in 3b and each pilot condition in 3c, which pilot gates have already been passed, and Dr. Anjali Rao decides go, no-go, or go only under stated conditions; it does not verify the checklist for the first time and does not approve the 11 January network rollout. |  |  |

# Part 4 · Release-Readiness Checklist v1

This is the scored work product. Write 25 to 40 rows. Every row needs all ten columns filled, including the phase it gates (Pilot, Network or Both).

## 4a. Header block

| Field | Your entry |
| --- | --- |
| Product / release | Beacon 1.4.x — AI-assisted patient triage, Kestrel Health Network |
| Phases gated | Pilot: Kestrel Riverside and Kestrel Hillcrest, 14 Dec 2026 · Network: all nine hospitals, 11 Jan 2027 |
| Checklist version | v1 · 08 Dec 2026 – U11910 – Robin Cherian |
| Governance structure | Every criterion answers: what is enforced · what evidence exists · where it is logged · who approves |
| Gate disposition rule | At every gate, each Not-met control is closed with evidence, deferred through Part 4c, or blocks the gate. Critical controls cannot be deferred. An expired deferral blocks the next gate. |
| Risk acceptance rule | Clinical AI risk is accepted only by Dr. Anjali Rao or Dr. Helen Mathews, in writing, with a review date, and recorded in the enterprise risk register (AIP-2). No one in the delivery team may accept risk on behalf of the release. |
| Contradiction rule | Where a claim (a tick, a signature or a team-channel message) and the evidence disagree, the status follows the evidence. The contradiction is logged in Part 4d with its source and a resolution owner, and the gate approver confirms the resolution. |
| Evidence standard | Every evidence item carries a stable reference (ID, version or commit, and date), is stored in the system named under "Where logged", is retained for 8 years under RP-1, and can be retrieved by someone outside the delivery team. Gate approvals are signed records, not channel messages, and are indexed under G-12. |
| Accountable owners by dimension | Business: Marcus Bell · Technical: Neha Sharma · Quality: Victor Osei · Governance: Dr. Helen Mathews · Operational: Priyanka Das |
| Purpose of the 10 Dec Go/No-Go meeting | The 10 December Go/No-Go meeting confirms, against the evidence recorded at each gate in 3b and each pilot condition in 3c, which pilot gates have already been passed, and Dr. Anjali Rao decides go, no-go, or go only under stated conditions; it does not verify the checklist for the first time and does not approve the 11 January network rollout. |

## 4b. Criteria

Write the three AI-control rows first. Each must state the stage and phase it gates, and: AI-01 Confidence threshold: the metric · the number · where the number came from (which data) · a named owner · what happens below it AI-02 Human-in-the-loop trigger: the condition that sends a case to a person · the named role that receives it · the time limit AI-03 Model drift monitor: what is measured · the baseline · the acceptable band · where the alert goes · who responds · the action on a breach

| ID | Stage | Phase | Dimension | Criterion (a checkable question) | Evidence required | Where logged | Accountable owner (named) | Approver | Status at 8 Dec + basis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AI-01 | Build | Both | Technical | Confidence threshold: metric = Beacon's confidence score for Routine and Self-care messages; number = 0.80, proposed by Dr. Farah Siddiqui from ev-118 (3,000 Kestrel messages, build 1.4.0) and to be re-evaluated on build 1.4.2 with the pinned model; owner Neha Sharma; below the threshold the message goes to the triage nurse queue. Does triage-config.yaml set auto_route_threshold to that evaluated, CSO-approved value? | Kestrel evaluation at the configured value; CSO approval record; configuration commit | triage-config.yaml (commit a41f, 26 Nov, and successors); evaluation reports (ev-118 and its replacement) | Neha Sharma | Dr. Helen Mathews | Not met. auto_route_threshold is 0.72, lowered on 25 Nov without re-evaluation or CSO approval (E3; E4, 26 Nov). |
| AI-02 | Spec | Both | Operational | Human-in-the-loop trigger: conditions = category Emergency or Urgent; Routine or Self-care below the AI-01 threshold; any patient reply to an automated message. Receiving role = triage nurse at the pilot site. Time limit = 30 minutes for Emergency, Urgent and patient replies; 24 hours for below-threshold Routine and Self-care (proposed). Is every trigger routed to a nurse and handled within its limit? | Routing configuration; night-shift queue simulation at the approved threshold showing limits met | triage-config.yaml; nursing rota and queue reports | Priyanka Das | Dr. Helen Mathews | Not met. The night-shift urgent peak takes about 75 minutes to clear against 30 (E4, 1 Dec); patient replies land in the general inbox, answered within 48 hours (E4, 3 Dec). |
| AI-03 | Build | Both | Operational | Model drift monitor: measures = under-triage rate from a weekly clinician sample of at least 200 auto-routed messages, overall and per language group; share auto-routed; category distribution. Baseline = ev-118 on Kestrel data (2.1% under-triage overall, 1.6% English-only, 6.8% mixed-language; 69% auto-routed at 0.80), replaced by the Q-01 re-run. Bands: overall under-triage amber above 2.6%, red above 3.1%; any language group red above the Q-02 limit; auto-route share amber outside ±5 points, red outside ±10 points. Alert pages the O-01 on-call responder; amber reviewed by Dr. Farah Siddiqui within 1 working day; red decided by Dr. Helen Mathews the same day, with auto-routing switched off so all messages go to nurses. Window: weekly. | Dashboard configuration with Kestrel baseline, sampling schedule and alert rules | Grafana "Beacon Drift" | Priyanka Das | Dr. Farah Siddiqui | Not met. Baseline is the CorvidBench supplier benchmark; no under-triage measure or sampling exists; alerts go to an unmonitored channel (E5). |
| B-01 | Intent | Both | Business | Do beacon/intent.md and the business case cover portal messages and automated replies, with sponsor approval? | Updated beacon/intent.md and business case with approval record | beacon/intent.md; board papers | Marcus Bell | Dr. Anjali Rao | Not met. intent.md covers GP referral letters only; scope was widened on 9 Oct by a team-channel decision (A5, Intent row). |
| B-02 | Intent | Pilot | Business | Are the pilot sites, Kestrel Riverside and Kestrel Hillcrest, agreed? | Executive minutes recording the decision | Executive minutes, September | Marcus Bell | Dr. Anjali Rao | Met. Agreed in the September executive minutes (Part B item 2), consistent with A2. |
| B-03 | Deploy | Network | Business | Is a separate network gate decision, based on pilot evidence, recorded before 11 Jan 2027? | Network gate decision record citing the Part 3c network conditions | Go/No-Go decision records, indexed under G-12 | Marcus Bell | Dr. Anjali Rao | Not met. The appendix says the network rollout proceeds per Rollout plan v2 once the pilot passes (Part B appendix; item 28). |
| T-01 | Spec | Both | Technical | Has an architecture review covering portal messages and automated replies superseded ADR-009? | Signed architecture review record | Architecture decision records | Neha Sharma | Kavya Nair | Not met. ADR-009 is dated 21 Sept, before the 9 Oct scope change, with no later review (E8, item 4). |
| T-02 | Plan | Both | Technical | Do approved plans exist for all 11 features, including automated reply drafting and threshold tuning? | Approved plan per feature | beacon/plans/ | Neha Sharma | Dr. Helen Mathews | Not met. Plans exist for 9 of 11 features; the two clinical features have none (A5, Plan row). |
| T-03 | Review | Both | Technical | Has every PR been reviewed by a human who did not write its prompts? | Independent review record for each PR, including the 12 approved by Imran Qureshi | Pull request system | Neha Sharma | Victor Osei | Not met. 12 PRs were approved by Imran Qureshi, who wrote the prompts that produced them (A5, Review row). |
| T-04 | Build | Both | Technical | Does triage-config.yaml pin an evaluated model version instead of a floating alias? | Configuration with pinned version; CSO approval of that version | triage-config.yaml (commit a41f and successors); contract CTR-311 | Neha Sharma | Dr. Helen Mathews | Not met. model is corvid-med-latest, which moves to corvid-med-3.3 on 15 Dec (E3; E4, 30 Nov; E8, CTR-311 clause 9.4). |
| T-05 | Deploy | Network | Technical | Has a load test passed at network volume for all nine hospitals? | Load test report at network volume | Performance test reports (LT-1.4.2 and its network-volume successor) | Neha Sharma | Victor Osei | Not met. LT-1.4.2 covers 3× pilot volume only (Part B item 15). |
| T-06 | Deploy | Both | Technical | Has rollback been rehearsed for application, model version, prompt version and a switch-off to manual triage? | Rollback rehearsal record for all four | Runbook §5; pipeline logs | Neha Sharma | Victor Osei | Not met. Only the application container was rolled back, 1.4.2 to 1.3.9 (E6). |
| T-07 | Review | Both | Technical | Has the penetration test passed, with its critical finding fixed and the retest signed? | PT-2026-77 report and signed retest | Security test records (PT-2026-77) | Neha Sharma | Victor Osei | Met. PT-2026-77: 1 critical finding fixed; retest passed 30 Nov, signed R. Menon (Part B item 13). |
| T-08 | Build | Both | Technical | Is build 1.4.2 complete, with all PRs merged? | Merged PR list for build 1.4.2 | Pull request system; CI (build 1.4.2) | Neha Sharma | Victor Osei | Met. 87 PRs merged; current build 1.4.2 (A5, Build row; Part B item 7). |
| T-09 | Deploy | Both | Technical | Does every item Tobias Grant owns have a named Kestrel owner from A3, with handover recorded before 18 Dec 2026? | Handover record naming each new owner | Checklist v1 owner column; handover log | Neha Sharma | Victor Osei | Not met. No successor is named; his contract ends 18 Dec (A3; Part B appendix ownership note). |
| T-10 | Build | Network | Technical | Has every model, prompt or threshold change since the pilot started, including the move to corvid-med-3.3, been re-evaluated on Kestrel data and approved before use? | Re-evaluation report and CSO approval for each change | Evaluation reports; change log | Neha Sharma | Dr. Helen Mathews | Not met. Corvid moves the alias to corvid-med-3.3 on 15 Dec, and no re-evaluation is planned (E4, 30 Nov). |
| Q-01 | Build | Both | Quality | Has Beacon been evaluated on Kestrel data on build 1.4.2, with the pinned model and the configured threshold? | Kestrel evaluation report replacing ev-118, reviewed by the CSO | Evaluation reports (ev-118 and its replacement) | Victor Osei | Dr. Helen Mathews | Not met. ev-118 covers build 1.4.0, corvid-med-3.2 and threshold 0.80; CSO review pending (E1 footer). Supplier summary is not Kestrel data (E2). |
| Q-02 | Spec | Both | Quality | Is an under-triage acceptance limit approved, overall and for each language group? | Signed acceptance criteria | Clinical safety case | Victor Osei | Dr. Helen Mathews | Not met. No limit is set; ev-118 shows 6.8% for mixed-language messages against 1.6% English-only (E1). |
| Q-03 | Plan | Both | Quality | Does the test strategy keep regression testing separate from model evaluation? | Test strategy document | QA records | Victor Osei | Victor Osei | Unknown. The test strategy is not in the pack; Victor Osei notes the regression suite excludes the evaluation set (E4, 27 Nov). |
| Q-04 | Review | Both | Quality | Is the regression suite green on build 1.4.2? | CI run result | CI system (run #2291) | Victor Osei | Victor Osei | Met. CI run #2291, 27 Nov, build 1.4.2 (E4, 27 Nov; Part B item 8). |
| Q-05 | Review | Both | Quality | Do evaluation results meet the Q-02 limits, including for mixed-language and transliterated messages? | Evaluation results against Q-02 | Evaluation reports | Victor Osei | Victor Osei | Not met. Mixed-language under-triage is 6.8%, logged as R-17 (E1). |
| Q-06 | Review | Network | Quality | Does a clinician sample of auto-routed pilot messages show under-triage within the Q-02 limits? | Clinician sampling results from the pilot | Grafana "Beacon Drift"; evaluation reports | Victor Osei | Victor Osei | Not met. The pilot has not started and no sampling is scheduled (E5). |
| G-01 | Review | Both | Governance | Is there a Kestrel clinical safety case and hazard log, covering automated replies, mixed-language messages and nurse queue capacity, signed by Kestrel's CSO? | Signed Kestrel safety case and hazard log | Clinical safety records (hazard log v2 retained as input) | Dr. Helen Mathews | Dr. Helen Mathews | Not met. Hazard log v2 is Corvid's, signed by Dr. P. Andrews; Dr. Helen Mathews has not been asked to review it (E7). |
| G-02 | Review | Both | Governance | Has every clinical AI risk, including R-17, been accepted or rejected in writing by the CMO or CSO, with a review date? | Signed risk acceptance with review date | Enterprise risk register (R-17) | Dr. Helen Mathews | Dr. Helen Mathews | Not met. R-17 was accepted by Neha Sharma (E4, 5 Dec and 7 Dec). |
| G-03 | Spec | Both | Governance | Is a DPIA addendum covering portal messages and automated replies approved? | Approved DPIA addendum | DPO records (DPIA v1 and addendum) | Dr. Helen Mathews | Grace Liu | Not met. DPIA v1 covers referral letters only (E4, 2 Dec). |
| G-04 | Build | Both | Governance | Does the decision record log category, confidence, rationale, model version, prompt version, threshold, routing action, reply text and nurse override? | log_fields configuration and one reconstructed decision | triage-config.yaml (commit a41f and successors); audit log store | Dr. Helen Mathews | Owen Fletcher | Not met. log_fields holds message_id, category and confidence only (E3). |
| G-05 | Build | Both | Governance | Are patient communications and decision records retained for 8 years? | Retention configuration export | triage-config.yaml (commit a41f and successors) | Dr. Helen Mathews | Owen Fletcher | Not met. retention_days is 365 (E3; A4, RP-1). |
| G-06 | Review | Both | Governance | Are automated self-care replies at reading level grade 8 or below? | Reading-level test on a sample of replies | Evaluation reports | Dr. Helen Mathews | Dr. Helen Mathews | Not met. A sample of 200 replies measured Grade 11 (E1). |
| G-07 | Deploy | Both | Governance | Does every automated reply tell the patient it was drafted by an automated system, in approved wording in English, Hindi and Marathi? | Approved disclosure wording in three languages | Communications records | Dr. Helen Mathews | Dr. Anjali Rao | Not met. Draft wording is with Legal, English only (E8, item 26). |
| G-08 | Spec | Both | Governance | Are the vendor contracts and data-processing agreements signed for Corvid AI and MedLink Systems? | CTR-311 and CTR-312 with DPAs | Contract records (CTR-311, CTR-312) | Dr. Helen Mathews | Grace Liu | Met. CTR-311 (Corvid) and CTR-312 (MedLink) signed; both DPAs include India data residency (Part B item 5). |
| G-09 | Review | Both | Governance | Is there a written rule that any model, prompt or threshold change affecting clinical output needs re-evaluation on Kestrel data and CSO approval before use? | Approved change-control rule | AIP-2 records; risk register | Dr. Helen Mathews | Dr. Helen Mathews | Not met. The appendix says the threshold "may be tuned operationally by Engineering" (Part B appendix). |
| G-10 | Review | Both | Governance | Are automated replies offered in the patient's chosen language (English, Hindi or Marathi)? | Reply samples in each language | Evaluation reports | Dr. Helen Mathews | Dr. Helen Mathews | Unknown. The pack does not show the languages replies are sent in (E1; A4, PCS-3). |
| G-11 | Review | Network | Governance | Is the hazard log updated with pilot incidents and re-signed before 11 Jan 2027? | Updated hazard log, signed | Clinical safety records | Dr. Helen Mathews | Dr. Helen Mathews | Not met. The pilot has not started, and no Kestrel hazard log exists yet (E7). |
| G-12 | Deploy | Both | Governance | Is there a versioned evidence index for each gate decision, retained for 8 years, from which someone outside the delivery team can retrieve every cited artefact? | Evidence index listing ID, version or commit, date and location for each artefact | Go/No-Go decision records | Dr. Helen Mathews | Dr. Anjali Rao | Not met. No index exists; v0.9 gate approvals are appendix notes (Part B appendix) and the R-17 acceptance is a team-channel message (E4, 5 Dec). |
| O-01 | Deploy | Both | Operational | Do drift and safety alerts page a named on-call responder? | Alert routing configuration and on-call rota | On-call tool; triage-config.yaml | Priyanka Das | Dr. Anjali Rao | Not met. #beacon-alerts has 14 members and is not on any on-call rota (E5). |
| O-02 | Deploy | Pilot | Operational | Have all 29 pilot-site triage nurses completed the Beacon training module? | Learning system completion report | Learning system | Priyanka Das | Dr. Anjali Rao | Not met. 11 of 29 (38%) had completed it on 7 Dec (E8, item 24). |
| O-03 | Plan | Both | Operational | Do patient replies to automated messages go to the triage nurse queue? | Routing configuration and a test message | triage-config.yaml; nurse queue | Priyanka Das | Priyanka Das | Not met. They land in the general inbox, answered within 48 hours (E4, 3 Dec). |
| O-04 | Plan | Both | Operational | Does the contact centre have call scripts and a route for patients who report worsening symptoms? | Approved call scripts and escalation route | Contact centre procedures | Priyanka Das | Priyanka Das | Not met. The contact centre received only an email with release notes (E8, item 25). |
| O-05 | Spec | Both | Operational | Does night-shift nurse capacity at both pilot sites meet the AI-02 time limit at the approved threshold? | Capacity model and queue simulation | Nursing rota and queue reports | Priyanka Das | Dr. Helen Mathews | Not met. Two night nurses need about 75 minutes to clear the 25-case peak (E4, 1 Dec). |
| O-06 | Deploy | Network | Operational | Have triage nurses at all nine hospitals completed Beacon training before 11 Jan 2027? | Learning system completion report | Learning system | Priyanka Das | Dr. Anjali Rao | Not met. Training has been assigned only at the pilot sites (E8, item 24). |

IDs: B = Business, T = Technical, Q = Quality, G = Governance, O = Operational, AI = the three AI-specific controls (fill in their stage, phase and dimension too). Stages: Intent · Spec · Plan · Build · Review · Deploy. Phases: Pilot (14 Dec 2026) · Network (11 Jan 2027) · Both. Status: Met / Not met / Unknown as of 8 December, with a one-line basis. Add or remove rows to reach 25 to 40.

## 4c. Deferred controls register

Rule: a control that is Not met at a gate is closed with evidence, deferred here, or blocks the gate. Critical controls cannot be deferred: AI-01, AI-02, AI-03, Q-01, Q-02, Q-05, T-04, G-01 to G-07, G-10 and O-03. A deferral needs a reason it is safe for the phase, a compensating control with an owner, a named approver (the CMO or CSO where clinical risk is involved, under AIP-2), an expiry no later than the next gate, and a signed record indexed under G-12. An expired deferral blocks the next gate. No deferral below has been approved as of 8 December.

| Control ID | Deferred to | Why deferral is safe for the pilot | Compensating control (ID, owner) | Approver (status at 8 Dec) | Expiry | Where recorded |
| --- | --- | --- | --- | --- | --- | --- |
| T-05 | Network gate | The pilot runs at two sites; LT-1.4.2 passed at 3× pilot volume (p95 1.8 s). | Pilot limited to Kestrel Riverside and Kestrel Hillcrest (B-02, Marcus Bell) | Victor Osei (not yet approved) | Network gate, before 11 Jan 2027 | Go/No-Go decision records (G-12) |
| T-10 | Network gate | No model change may be used during the pilot without re-evaluation. | Model version pinned (T-04, Neha Sharma) | Dr. Helen Mathews (not yet approved) | Before any model change is used, and no later than 11 Jan 2027 | Evaluation reports; change log (G-12) |
| Q-03 | Network gate | Regression and evaluation evidence are recorded separately in Q-04 and Q-01. | Q-04 and Q-01 recorded as separate artefacts (Victor Osei) | Victor Osei (not yet approved) | Network gate, before 11 Jan 2027 | QA records (G-12) |
| Q-06 | Network gate | Pilot sampling can only be measured once the pilot runs. | Weekly clinician sampling during the pilot (AI-03, Priyanka Das) | Victor Osei (not yet approved) | Network gate, before 11 Jan 2027 | Grafana "Beacon Drift" (G-12) |
| G-11 | Network gate | Pilot incidents can only be added once the pilot runs. | Signed Kestrel safety case before the pilot (G-01, Dr. Helen Mathews) | Dr. Helen Mathews (not yet approved) | Network gate, before 11 Jan 2027 | Clinical safety records (G-12) |
| O-06 | Network gate | Nurses outside the two pilot sites receive no Beacon cases before 11 Jan 2027. | All pilot-site nurses trained (O-02, Priyanka Das) | Dr. Anjali Rao (not yet approved) | Network gate, before 11 Jan 2027 | Learning system (G-12) |

## 4d. Contradiction log

Each row is a v0.9 claim that the evidence contradicts. Status follows the evidence, never the claim. The resolution owner closes the gap, the approver confirms it in the 4b row, and the claim's source is told of the correction. Team-channel statements are listed as claims, not evidence.

| # | v0.9 claim (item and source) | Contradicting evidence | 4b row and status | Resolution owner | Confirmed by | Record |
| --- | --- | --- | --- | --- | --- | --- |
| C1 | Item 6 "Feature plans complete" ✓ | Plans exist for 9 of 11 features (A5, Plan row) | T-02: Not met | Neha Sharma | Dr. Helen Mathews | beacon/plans/ |
| C2 | Item 9 "Model validated (96% accuracy)" ✓, Corvid validation summary | Kestrel ev-118 accuracy 0.93; supplier data is US and UK (E1, E2) | Q-01: Not met | Victor Osei | Dr. Helen Mathews | Evaluation reports |
| C3 | Item 10 "Confidence threshold set (0.80)" ✓; "Eval numbers will be basically the same" (E4, 26 Nov) | auto_route_threshold is 0.72 since 25 Nov (E3) | AI-01: Not met | Neha Sharma | Dr. Helen Mathews | triage-config.yaml (commit a41f) |
| C4 | Item 11 "Clinical safety case signed" ✓ | Hazard log v2 signed by Corvid's CSO; Kestrel's CSO not asked (E7) | G-01: Not met | Dr. Helen Mathews | Dr. Helen Mathews | Clinical safety records |
| C5 | Item 14 "DPIA approved" ✓ | DPIA v1 covers referral letters only (E4, 2 Dec) | G-03: Not met | Dr. Helen Mathews | Grace Liu | DPO records |
| C6 | Item 16 "Accessibility review" N/A, "Backend service" | Beacon sends automated replies to patients, at Grade 11 (A2, E1) | G-06: Not met | Dr. Helen Mathews | Dr. Helen Mathews | Evaluation reports |
| C7 | Item 17 "Urgent → nurse queue, 30-minute response" ✓ | About 75 minutes to clear the night-shift peak (E4, 1 Dec) | AI-02: Not met | Priyanka Das | Dr. Helen Mathews | Nursing queue reports |
| C8 | Item 18 "R-17 accepted 5 Dec" ✓; "accepted … on behalf of delivery" (E4, 5 Dec) | Accepted by Neha Sharma, not the CMO or CSO (E4, 7 Dec; A4, AIP-2) | G-02: Not met | Dr. Helen Mathews | Dr. Helen Mathews | Enterprise risk register (R-17) |
| C9 | Item 22 "Data retention configured" ✓, 365 days | RP-1 requires 8 years (A4) | G-05: Not met | Dr. Helen Mathews | Owen Fletcher | triage-config.yaml |
| C10 | Item 24 "Triage nurses trained" ✓ | 11 of 29 pilot-site nurses completed (E8) | O-02: Not met | Priyanka Das | Dr. Anjali Rao | Learning system |
| C11 | Item 26 "Patient communication (AI disclosure) approved" ✓ | Draft with Legal, English only (E8) | G-07: Not met | Dr. Helen Mathews | Dr. Anjali Rao | Communications records |
| C12 | Item 27 "Vendor model-change process agreed" ✓; Corvid "non-material improvement" (E4, 30 Nov) | Floating alias moves to corvid-med-3.3 on 15 Dec; AIP-2 requires re-evaluation and CSO approval (E3, E8, A4) | T-04: Not met | Neha Sharma | Dr. Helen Mathews | triage-config.yaml; CTR-311 |
| C13 | Item 30 "All stage gates already approved — formality" | Every gate approved by Neha Sharma on 2 Dec, including clinical safety (Part B appendix) | G-12: Not met; gates re-approved per Table 3b | Dr. Helen Mathews | Dr. Anjali Rao | Go/No-Go decision records |

# Part 5 · Readiness statement to the sponsor

No more than half a page, addressed to Dr. Anjali Rao. Give one decision for 14 December that she can act on: go, no-go, or go only under stated conditions, with each condition specific, owned and checkable. Write it so that it could be forwarded to the regulator unchanged.

| Heading | Your text |
| --- | --- |
| To | Dr. Anjali Rao, Chief Medical Officer — Programme Sponsor |
| My decision for 14 December (go / no-go / go only if…) | No-go for the pilot on 14 December 2026. Beacon should not process patient messages until the conditions below are met. A reduced-scope pilot is not available: the manual-triage switch-off is untested (T-06), and G-01, G-03, G-04 and G-05 apply to any use. This follows the 4a gate disposition rule: Critical controls cannot be deferred (4c). |
| Why: what is ready and what is not | Ready: pilot sites (B-02), penetration test (T-07), build 1.4.2 (T-08), regression suite (Q-04), vendor contracts and DPAs (G-08). Not ready: 32 of 40 criteria. Most serious: no Kestrel safety case (G-01); 6.8% mixed-language under-triage with no approved limit (Q-02); unevaluated 0.72 threshold and corvid-med-latest model (AI-01, T-04); about 75 minutes to clear the night urgent queue against 30 (AI-02). |
| What would make it a yes (each condition specific, owned and checkable) | All confirmed before a rescheduled Go/No-Go, dated by Dr. Anjali Rao on 10 December 2026. Evidence in brackets. 1. Owner Dr. Helen Mathews, confirmed by Dr. Helen Mathews: G-01 Kestrel safety case and hazard log signed (signed hazard log); G-06 replies at grade 8 or below (reading-level sample). 2. Owner Dr. Helen Mathews, confirmed by Owen Fletcher: G-02 R-17 accepted or rejected with a review date (risk register); G-04 full decision record logged (reconstructed decision); G-05 8-year retention (configuration export). 3. Owner Dr. Helen Mathews, confirmed by Grace Liu: G-03 DPIA addendum for portal messages (approved addendum). 4. Owner Dr. Helen Mathews, confirmed by Dr. Anjali Rao: G-07 AI disclosure in English, Hindi and Marathi (approved wording). 5. Owner Neha Sharma, confirmed by Dr. Helen Mathews: T-04 model version pinned; AI-01 threshold equals the evaluated, approved value (triage-config.yaml). 6. Owner Victor Osei, confirmed by Dr. Helen Mathews: Q-01 build 1.4.2 evaluated on Kestrel data; Q-02 under-triage limit approved, overall and per language; Q-05 results meet it (evaluation report). 7. Owner Priyanka Das: AI-02 night-shift capacity meets the 30-minute limit (queue simulation), confirmed by Dr. Helen Mathews; O-03 patient replies reach the nurse queue (routing test), confirmed by Priyanka Das; AI-03 drift monitor with Kestrel baseline and weekly sampling (Beacon Drift configuration), confirmed by Dr. Farah Siddiqui. 8. Also Met in 4b: T-01, T-02, T-03, T-06, T-09, O-01, O-02, O-04, G-10. |
| What must be true before 11 January | The network rollout needs its own decision by Dr. Anjali Rao before 11 January 2027 (B-03, Marcus Bell). It requires: network-volume load test (T-05, Neha Sharma); CSO-approved re-evaluation of any model change, including corvid-med-3.3 (T-10, Neha Sharma); pilot sampling within Q-02 (Q-06, Victor Osei); re-signed hazard log (G-11, Dr. Helen Mathews); training at all nine hospitals (O-06, Priyanka Das). |

# Part 6 · Assumptions

Anything you assumed that the case did not state, for example a tolerance figure you proposed. Leave it empty if you made no assumptions.

| # | What I assumed | Why I needed to assume it |
| --- | --- | --- |
| A1 | Part 2 (item 13): penetration test PT-2026-77 covers build 1.4.2. | The pack does not name the build tested; the retest passed on 30 Nov, after CI run #2291 on build 1.4.2 (27 Nov), so T-07 is marked Met on that basis. |
| A2 | Part 2 (item 5): the DPAs in CTR-311 and CTR-312 cover the portal-message data flows. | The pack confirms the DPAs are signed with India data residency but does not state their scope, so G-08 is marked Met on the evidence available. |
| A3 | Part 2, F7: R-17 (mixed-language under-triage) is a clinical risk under AIP-2. | AIP-2 limits acceptance of clinical AI risks to the CMO or CSO; the pack does not classify R-17, but it concerns urgent patients being under-triaged. |
| A4 | Part 2, F29: the v0.9 stage "Release" corresponds to the Deploy stage of the artefact chain. | v0.9 uses Intent, Spec, Plan, Build, Review, Release, while A5 uses Deploy; mapping is needed to compare the two. |
| A5 | Part 3: everyone in A3 except Tobias Grant is available through 11 Jan 2027. | The pack gives a contract end date only for Tobias Grant (18 Dec 2026) and no leave dates for anyone else; owners and approvers must be available for their phase. |
| A6 | Part 3b, 4b T-01: Kavya Nair approves the architecture review. | A3 lists no other architect once Tobias Grant leaves, and ADR-009's author should not approve its replacement. |
| A7 | Part 3c, 4b T-05: "network volume" for the load test is to be defined by Kavya Nair and Victor Osei. | The pack gives only pilot volume (LT-1.4.2 at 3× pilot volume) and no figure for all nine hospitals. |
| A8 | Part 4b AI-02: time limits are 30 minutes for Emergency, Urgent and patient replies to automated messages, and 24 hours for below-threshold Routine and Self-care messages. | The 30 minutes is the target stated in v0.9 item 17; the pack gives no limit for below-threshold cases, so 24 hours is my proposal, shorter than the 48-hour general inbox (E4, 3 Dec). |
| A9 | Part 4b AI-03: bands are overall under-triage amber above 2.6% and red above 3.1%; auto-route share amber outside ±5 points and red outside ±10 points; amber reviewed within 1 working day, red decided the same day. | The pack gives no band; these are my proposals, set 0.5 and 1.0 points above the ev-118 baseline of 2.1%, to be approved by Dr. Farah Siddiqui and Dr. Helen Mathews. |
| A10 | Part 4b AI-03: the monitor uses a weekly clinician sample of at least 200 auto-routed messages. | The pack schedules no sampling (E5); 200 mirrors the sample size used for the reading-level test in E1. |
| A11 | Part 4b AI-03: ev-118 is the interim baseline until the Q-01 re-run replaces it. | No Kestrel baseline is loaded (E5), and ev-118 is the only Kestrel evaluation, though it ran on build 1.4.0 at threshold 0.80. |
| A12 | Part 4b T-08: Victor Osei approves "build 1.4.2 complete" rather than the 3b Technical Build approver, Dr. Helen Mathews. | The 3b Technical Build gate is a clinical approval of configuration; a code-completeness check sits with the QA Manager. |
| A13 | Part 5: showing nurses Beacon's category and rationale counts as influencing patient care under CSS-1. | This is why a reduced-scope pilot, with automatic routing and automated replies off, still needs the Kestrel safety case (G-01). |
| A14 | Part 5: the rescheduled Go/No-Go date is set by Dr. Anjali Rao at the 10 Dec meeting. | The pack gives no durations for closing the conditions, so the statement does not propose a date. |
| A15 | Part 4c: the network-only controls (T-05, T-10, Q-03, Q-06, G-11, O-06) can be deferred to the network gate. | Sites and nurses outside the pilot receive no Beacon cases before 11 Jan 2027, and each deferral has a compensating control in place for the pilot. |

# Before you submit

Tick each box only if it is true. Every "no" is a mark you can still recover.

| Check | Done? |
| --- | --- |
| Part 1: the cover block is complete | ☐ |
| Part 2: 15 or more findings, covering all five dimensions; the example row is deleted | ☐ |
| Part 3: one named Accountable person for each dimension; no teams, suppliers, leavers or "TBD" | ☐ |
| Part 3: the pilot gate and the network gate are stated separately (3c) | ☐ |
| Part 4: 25 to 40 rows, with three separate AI-control rows (AI-01, AI-02, AI-03) and every field filled | ☐ |
| Part 4: every row has a stage and a phase, and all six stages are used | ☐ |
| Part 4: every row names its evidence and where it is logged | ☐ |
| Part 4: statuses are as of 8 December and match the evidence: "Met" only where the evidence shows it, "Not met" where it says so | ☐ |
| Part 4: the header says the Go/No-Go confirms gates already passed | ☐ |
| Part 5: one decision for 14 December the sponsor can act on, with what must be true before 11 January, in half a page or less | ☐ |
| Nothing important is only in an image or only in your head | ☐ |

Submit this file, named UST_AITPM_Week1_Ex2_Workbook_<your candidate id>, through the submission process your facilitator gives you. Do not paste screenshots in place of text.